## Sheet1
REQ ID | Requester | Comments | Status | Comments
1 | Liu, Yuan-1 | For Different Department, need define differnt Application type | Confirm
2 | Liu, Yuan-1 | Main Document need upload mutiple document | Waiting Confirm | Ansen Need check with Global Team
3 | 寇红运 | Person is not relate to Brand, only relate to department, user can select user by Department |  | Ansen Need check with Global Team
4 | 寇红运 | Need Build a UI to see Potential Approver by Brand without in process | Confirm
5 | 孟彤 | find an easy way to find my request | Confirm
6 | 孟彤 | we can modify the approver when request in process | Waiting Confirm | Based on Complaince request, we cannot do this change
7 | 许晟静 | Need access control by brand/ departement/ | Waiting Confirm
8 | 张明 | It usually happens that the review person could not find the task via email link, and have to log on system to find task, hope it could be improved. Once request is closed, need send mail to user to notify process is closed, need show approve log and comments in mail once date is overdue, need daily reminder | Confirm
9 | Hou Rong | Suggest to improve the user interface to only list the requests related to the user account. 2~3 Key users could be set to oversee all of the ongoing requests, meawhile, a DRA manager/CCDO could only see the requests initiated by her and the requests need her review and approval. E.g. Rong is key user, Rong could see of the request in her working panel. Ansen is a DRA manager, he could only see the requests he initiated and the requests need his review and approval. | Confrim
10 | Hou Rong | To revise application type (response to Yuan Liu’s comments): “label”  “label/FB/Foils/blister” | Confirm
11 | Shenjie | Need support iPhone to access new system. | Confirm
12 | Shenjie | Need Remind mail for system process. Detail remind cycle and template will be defined at following meeting. | Confirm
13 | Shenjie | if process status is overdue, still need this process can be review/Approval | Confirm
14 | Shenjie | The default Approval method is parallel | Confirm
15 | Shenjie | Need Provide a UI for Search all department’s all product. Since we need implement different department has different product To avoid create duplicate product, user want to have a UI to see other department's product list | Confirm
16 | Hou Rong | product cannot be disable, not impact to history data and search, but need impact at create page | Confirm
17 | Hou Rong | Product list need sort | Confirm
18 | Hou Rong | need provide a list to see my approved closed request, my submit closed request,my request is in process | Confirm | Ansen Need check with Global Team
19 | Hou Rong | need check the file size before upload file | Confirm
20 | Hou Rong | 需要在Approval/submit的边上加个文本框，或者弹出对话框，具体内容需要可以维护 add a popup windows to show text wiht ok and cancel button, the text need can be maintenance | Confirm
Follow Up | 1 | Ansen约个会去讨论confidence的问题
| 2 | Ansen根据目前的Operation Module去进行support优化